## Sheet1
TETSWOTH CLP - ACTION CHART (As at April 2021)
Serial | Action | Status | Who | How | When | Progress
2021-04-01
1 | Reflect local opinion on preferred nature and extent of new building in the village | Ongoing | TPC | Commenting on planning proposals for additional development | Ongoing | Significant PC input to major development proposals and pursuit of enforcement action. Tetsworth Community email list and Facebook page for local planning issues.Neighbourhood Plan at Referendum stage 6 May 2021
2 | Encourage beneficial community use of Section 106 or CIL funding from any major housing proposals | Ongoing | TPC | Publicise CIL payments expected from Mount Hill Farm and other hosuing developments | Ongoing | Recognised benefits of launching Neighbourhood Plan to yield 25% CIL payments. PC invited suggestions and created candidate list. PATCH refurbishment project and speed warning signs already implemented, others in pipeline
3 | Reflect local opinion on establishing new businesses in Tetsworth | Ongoing | TPC | Commenting on planning proposals for business development | Ongoing | Business survey as part of Neighbourhood Plan evidence collection via Questionnaire, Spring 2017. Mobile Post Office visiting weekly since April 2018. Proposal for Zioxi premises expansion
4 | Implement kitchen and upper floor refurbishment projects | Underway | Memorial Hall Committee | Complete refurbishment plans as funding permits | Within 5 years | Plans developed, tender documents prepared and some grant funding approved. Heating and insulation upgraded, kitchen equipment chosen
5 | Consider villager opinion on future churchyard burial policy | Ongoing | PCC | Decide on future burial policy | Within 1 year | Preference for reuse of old unmarked grave plots noted when space becomes critical in a few years
6 | Consider reintroduction of regular bell-ringing | For consideration | Volunteers and Bell Captain | Form bell-ringing team | Within 2 years | Bells rung on request for specific occasions, but routine ringing by village volunteers unlikely
7 | Investigate viability of building 'Trim trail' round the edges of the Village Green | New initiative | Future Trail users, TSSC & TPC | Consider funding and location | Plan within 1 year | Purchase and installation of adult exercise equipment achieved as part of PATCH (play area) refurbishment project
8 | Launch a project to refurbish the PATCH play area | New initiative | Parents, volunteers and TPC | Seek funding and develop plan | Plan within 1 year | Complete refurbishment and installation of new play equipment achieved by end 2018
9 | Consider extended school hours with more extra-curricular wrap-around activities | New initiative | Governors and staff | Assess viability and develop plan | Consider within 1 year | After school clubs running on 4 days a week with some professional support for sports. Programme interrupted by Covid constraints
10 | Encourage more local and youth participation in organised sports teams | Ongoing | TSSC | Rolling advertising campaign | Ongoing | Sports teams seeking additional players. Representative football and cricket teams come from outside Tetsworth
11 | Consider expanding the range of sports supported | New initiative | New sports proposers and TSSC | Assess viability, plan, fund and implement | Assesss within 1 year | Sports programme still dominated by football and cricket teams in season. Resurrection of tennis area recently suggested.
12 | Consider viability of enhancing sports facilities and infrastructure | New initiative | Potential users, TSSC | Assess viability, plan, fund and implement | Assess within 1 year, implement in 5 | Adult exercise equipment installed as part of PATCH upgrade project. Football pitch improvements achieved in 2018. New ground maintenance equipment purchased
13 | Plan, launch and sustain new group activities and clubs | New initiative | Activity proposers | Assess viability, plan, fund and implement | Ongoing | More exercise-related sessions operating from Memorial Hall. Progress suspended by Covid constraints
14 | Achieve better coordination and advertising of village events | New initiative | Event sponsors and organisers | Develop a comprehensive village events diary | Wihin 1 year, then update regularly | More active Newsletter, Facebook and Twitter use, but TPC website little used for this. No comprehensive village calendar published so far
15 | Identify individuals or groups in need of help from the Cozens Bequest | Ongoing | All residents | Advising Trustees of need | Review regularly | Trustees have accepted broader requests for support
16 | Plan and implement a Tetsworth Good Neighbour scheme | New initiative | Scheme sponsors and supporters | Plan and implement scheme with volunteers | Plan within 1 year, implement in 2 | No volunteers willing to initiate scheme, but Tuesday Coffee Shop in Village Hall provides network for some older residents. Active support network established in response to Covid pandemic.
17 | Submit a broader range of articles for publication in the Tetsworth Newsletter | New initiative | Organisation and individual authors | Submit regular or occasional articles | Ongoing | Some evidence of wider editorial coverage. Publication interrupted by Covid constraints
18 | Create a 'one-stop-shop' Tetsworth website linking existing information source | New initiative | Volunteer webmaster and feeder website managers | Design, launch and sustain an overal village website | Plan and implement within 1 year | Website structure and material refreshed during 2018, but still dominated by TPC business. Links to other village organisations created. PC appointing councillor to lead digital communications
19 | Create a new Tetsworth Business Directory | Revision of previous edition | Volunteers with TPC guidnace | Identify businesses, prepare and publish | Within 1 year, then update regularly | Contributions canvassed via TPC website, good range of local businesses now listed
20 | Create a New Residents' Welcome Pack | New initiative | Volunteers with TPC guidance | Plan content, prepare and publish | Within 1 year, then update regularly | No progress, but still possibility for inclusion under TPC website
21 | Hold an annual Clubs and Societies fair | New initiative | participating organisations | Organise alongside existing village event | Annually | Limited coordination, but organisations promote activities at Annual Parish Meeting
22 | Create a Visitors' Information Point | New initiative | Volunteer proposers | prepare content, site noticeboard and display | Implement within 1 year | No progress to date, but public information posted on PC noticeboard sited outside Memorial Hall. Larger noticeboard on order
23 | Research the history of those commemorated on Tetsworth War Memorial | Ongoing | Volunteers | Research source material and publish findings | Complete within 2 years | Booklet published by Tony Honeyman in Nov 2017. Copies distributed to public bodies and available for individual purchase.
24 | Collate Tetsworth parish archives | New initiative | Volunteers with TPC guidnace | Collate source material into structured framework | Within 2 years, then maintain | Some particular items reviewed, but no consolidated project yet in place. Importance raised due to wholesale personnel changes on TPC. Village history project launched in 2020.
25 | Dispose of dog fouling responsibly | Ongoing | Dog owners and walkers | Use disposal bins | Ongoing | Constant vigilence, Newsletter articles. Annual village litter-pick established in March 2019
26 | Regular campaign to encourage responsible on-street vehicle parking | Ongoing | Police, TPC and vehicle users | Publicity campaign | Regular reminders | School parking issue raised with staff and local PCSO. Police also advised of inconsiderate High St parking. Parking policy in Tetsworth Neighbourhood Plan
27 | Consider a local gas supply network as a candidate project which might qualify for CIL funding | New initiative | TPC and residents | Considerration of major house-building planning applications | Ongoing | Only achievable as result of major development. No momentum in foreseeable future
28 | Monitor progress of Better Broadband for Oxfordshire roll-out | New initiative | TPC | Review of project website | Completion within 1 year | Fibre cabinets installed, service now available
29 | Report utility problems to service providers | Ongoing | Residents suffering utility problems | Reporting for compensation | Ongoing | Responsibility of individual householders. No chronic problems noted
30 | Resolve Swan gardens/Cygnet Close sewage smells | Current issue | Affected residents | Identify problem And agree solution | Plan within 1 year | Unsighted on progress
31 | Conduct village-run random speed checks | Current issue | Volunteers with TPC support | Negotiate wth Thames valley Police | Within 1 year, then regularly | Refresh TVP Community Speed Watch training planned, but held up by Covid constraints. 30mph and school 20mph flashing signs installed in 2020. 30mph bin stickers purchased and distributed. Reintroduction of double white lines on A40 in village being considered.
32 | Report location of potholes promptly | Ongoing | Residents suffering utility problems | Report on 'Fix My Street' website | Ongoing | Fix my Street' reporting link on TPC website
33 | Seek more helpful scheduling of OCC footpath clearance programme | Current issue | TPC | Negotiate with OCC | Annually | Advised will benefit from seasonal change in rolling programme. A40 footpath both sides of village cleared by OCC Mar 2021
34 | Plan self-help cobble-footpath maintenance | Ongoing | Volunteers and TPC | Regular volunteer working parties | Ongoing as required | Weed-killing maintenance now included in village grass-cutting contract
35 | Prepare map of local footpaths for recrerational use. Report access difficulties | New initiative | Volunteers | Prepare leaflet, report issues | Wihin 1 year, then ongoing | Volunteer Parish Footpath Warden retired 2020. No new incumbent yet. OCC footpaths map suggested for posting on TPC website map available yet
36 | Investigate Sustrans or other funding support for Judds Lane upgrade as a cycle path | New initiative | Proposal supporters | Seek funding and assess viability of scheme | Assess within 1 year, implement in 5 | Judds Lane resident has implemented upgrade to route surface. No approach to Sustrans yet
37 | Resist any reduction in existing bus services | Ongoing | Service users and TPC | Lobby councils and service providers | Ongoing | OCC support for Routes 124 and 275 ceased in 2016. Route 124 to Thame withdrawn. Saturday Route 275 service added in Sep 2020.
38 | Investigate viability of attracting additional commercial and public services to the village | New initiative | Proposal supporters with TPC guidance | Approach potential suppliers of service | Initial investigation within 1 year | Potential future services included in Neighbourhood Plan questionnaire. However, status as smaller village unlikely to attract significant public service investment
39 | Resist withdrawal of visiting library and play-bus services | Ongoing | Service users | Lobby councils and service providers | Ongoing | Mobile Children's Centre visits for 1.5 hours fortnightly. Mobile Library withdrawn. No service due to Covid constraints
40 | Lobby authorities for full resurfacing of M40 with lower-noise asphalt at earliest opportunity | New initiative | All concerned residents | Write to MP and councillors | Until full resurfacing implemented | Active support of M40CEG efforts. Resurfacing with lower noise asphalt completed late 2016. Only marginal noise mitigation achieved
41 | Consider development of a not-for-profit enterprise to install solar/acoustic barriers alongside the M40 | New initiative | Tetsworth M40CEG representative | canvass local support | Initiate within 1 year | Highways Engand cancelled photo-voltaic barrier plans for M40, no publicly funded barrier for Tetsworth in revised programme. Pilot scheme for barriers elsewhere implemented
42 | Reflect local opinion on alternative energy source planning applications | New initiative | TPC | Reflect local opinion | On receipt of planning proposals | Small solar farm introduced at Oxfordshire Golf Club. Planning applications for two major solar farms covering more than 100Ha south of M40 under consideration. Another 100Ha+ solar farm proposed for land north of A40 towards Milton Common. Cumulative environmental impact flagged up
43 | Plan and implement a village orchard | New initiative | Proposers with TPC guidance | Investigate sites and funding | Investigate within 1 year | No progress yet. Just one apple tree outside Memorial Hall. Concerns over maintenance responsibilities
44 | Plan and implement additional allotments | New initiative | Would-be allotment holders with TPC cooperation | Identify potential sites | Investigate in 1 year | Existing allotments now have single tenant. No waiting list, so need not proved
45 | Plant additional blubs in village verges | Continuing initiative | Volunteers with TPC guidance | Volunteer working parties | Annually | Community project launched Mar 2021. TPC financial support requested
46 | Report progress on actions to the Annual Parish Meeting | New initiative | Action holders with TPC prompting | Report to Annual Parish Meeting | Annually | Sixth year report prepared April 2021